## Sheet1
Task | Start (Week) [0-6] | Duration (weeks)
Sign Up page | 0 | 1
Login page | 0 | 1
Logout Page | 0.5 | 0.5
General Posts Feed page | 1 | 1
Profile Page | 1 | 1
Session functionality | 2 | 1
Individual Class Feeds | 3 | 2
Follow Functionality | 3 | 2
Profile Page | 3 | 2
Password Encryption | 4 | 1.5
Email Verification on Sign Up page | 5 | 1.5
Private Chat | 5 | 1.5
Website Styling | 5 | 1
Commenting | 6 | 1
Bug Fixing | 6 | 1.5
Prepare Final Documents | 6 | 1.5
current week = 3